Schoolyard Habitat Project Considerations & Timeline

The planning process should begin with brainstorming projects that the group feels would benefit the school and the school community. The next step should be focusing in on realistic objectives and deciding on one project idea. Project logistics should include picking a date for the implementation of the project and working backwards on the calendar to set milestones so that objectives are completed within the timeframe. At times, members of the planning team will assist in the completion of tasks between planning meetings (e.g., sharing plans with others not on the team, soliciting donations, researching fundraising opportunities, recruiting volunteers, ordering materials, etc.). The group’s ability to be disciplined in setting and meeting milestones will determine the effectiveness of the group. Milestones must also be set for the maintenance of the project after its completion.

  Things to Consider for the Habitat Project

As you know, the goals of the Schoolyard Discovery habitat projects are to:

- Increase the wildlife and plant habitat at each school

- Enhance educational opportunities for teachers and students by creating places for outdoor learning

- Create places of passive recreation and gathering for community residents

As you prepare to plan for and develop design plans for the project, consider the following:

- What are the current uses of your schools outdoor spaces?

- How would you like to use the school grounds for educational purposes?

  - Hands-on natural science activities, such as planting?

  - Exploration and discovery: inquiry-based learning?

  - Outdoor classroom: science, math, social studies, art, English, reading, writing, etc.?

    - Where might any of the above activities be located on the school grounds?

    - Are there particular areas of the school grounds (drainage areas, storm water runoff, expanses of asphalt or mowed grass) that would benefit from environmental enhancement?

    - What types of gardens and landscaping would encourage passive recreation (strolling, reflection, gathering) by community residents?  Where might these be best located on the school grounds?

As you consider the above questions, keep the following issues in mind:

- Traffic patterns  Where do children, community members and others walk?  Where do vehicles drive?

- Play spaces  Where are the play areas, competitive sports activities or recreational activities held?

- Visibility  Are there places on the school grounds that are hidden from view or are overgrown with vegetation?  Are there spaces on the school grounds you would like to cover up?

- Access  How will teachers and students use the space?  How will community members use the space?

- Solar orientation  Is it predominately sunny or shady?  Does the available sunlight change over the course of the year?

- Drainage  Does the area collect water? Does it drain water quickly?

- Maintenance  How is the area currently maintained? How do you envision the gardens and plantings to be maintained (by a committee, by individual classes, etc.)? Is there access to water?

- I have profiles of projects by theme complete with native plant suggestions and project consideration/development. Project themes include:

- Rain Gardens

- Habitat Gardens

- Vegetable Gardens

- Shade Gardens

- Butterfly Gardens

- Maryland Meadows

- Bird Gardens

- 5 Senses Gardens

- Winter Gardens

For these profiles email hobbsr@explorenature.org

  Children & Wildlife (and their Habitats)

Safety

- The type of plants you place in the habitat will attract a variety of different species of wildlife, even those you didn’t intend on attracting.  For example, planting flowering plants for butterflies will also attract bees, which may be a concern to be addressed.

- Be careful of any plants that will have thorns or prickers.

- Some plants are poisonous as well and not a good idea for gardens like “5 senses” which encourage children to touch.

Durability  The plants you choose will need to be somewhat hardy, especially if there is a chance that children will use them as play things.

Maintenance  Who will take care of the garden/habitat to make sure that the plants aren’t over-grown and weedy looking (especially over the summer months)?  Over-grown plants are the easiest way to lose support for a project, especially if it makes a play space unattractive.  Of course, the opposite is also true: the more beautiful and pleasant a space, the more support it will receive.

Animals Anything bigger than songbirds and insects may be unwelcome.  As stated above, it will be virtually impossible to keep unwanted animals away, especially if the basic components of habitat are provided and the play space is attached to a wooded area.  But if children visit the space frequently enough, the animals will sense the presence of humans and generally stay away.  The most “dangerous” animals (e.g., opossum and raccoon) are out at night anyway and won’t run into trouble with children in the play space (unless an animal is sick, which isn’t really something you can protect against).

  Questions to Consider as Planning Begins

- What partners are you going to invite to your planning team?

- Individuals and Organizations  Who needs to be involved?

- Remember more partners mean more ownership but also more “cooks in the kitchen.”

- Who is going to invite them and how?  By phone, letter, presentation?

  - How will you present your project ideas to the:

- Principal?

- PTO or PTA?

- Students?

- Other teachers?

- Community Groups?

- Others?

- When will you present your ideas to these groups (e.g., “Back to School” Night, the first day of    science class, etc.)?

- What day of the month are you going to meet (e.g., first Wednesday of every month)?

  - Set time and hold to it  consistency will equal success for this type of project

    - What are the top two spaces in which you most want to work at your school?

  - List approximate dimensions and the current condition of the sites

  - When will you decide what space to begin with?

- What types of projects would you like to do in those spaces?

  - When will you decide what project to focus on?

    - What are some possible funding sources for your project?

  - What contacts and connections do you have that can give you donations of services, materials or equipment?

- How will building these projects be incorporated into the curriculum?

  - Try to use examples as specific as possible based on your school

    - What educational purposes will the project serve after it is in the ground?

  - for the school?

  - for the community?

- When will you celebrate your successful project?

- How will the project be maintained (watering, weeding, monitoring, trash and debris removal, etc.)?  Who will do the maintenance?

  General Timeline for First Year

While each planning team will move at its own pace, there are several milestones that should be accomplished by a particular point in the school year. This timeline should be used in conjunction with other “toolkit” documents like the “Funding A Schoolyard Garden” document. The list below outlines general milestones and accomplishments to consider:

August

- Contact people interested and begin to schedule meeting times.

###### September

- Communicate with and obtain support from principal/administration

- Recruit planning team members (e.g., via presentation at faculty meeting)

- Introduce planning team objectives and asked for feedback from parents at “Back-to-School” Night

- Planning team begins regular monthly meetings

- Begin to brainstorm project ideas

- Look through the “Funding A Schoolyard Garden” document.

October

- Continue to brainstorm project ideas

- Begin to solicit input from others outside the planning team regarding design ideas

- Begin to formulate draft budgets for project ideas

- Develop a school year calendar with specific milestones including a project implementation date (date for student planting as well as a preparation date on a weekend before where parents, planning team member and other adult volunteers can prepare the site for planting) and work backwards.

- Begin to develop a fundraising plan

November

- Decide on a project, considering objectives

- Begin discussion of curriculum integration and student participation

- Continue to solicit input from others outside the planning team regarding design ideas

- Ask project advisors for input and design plans (if they can not be generated by planning team members)

December

- Continue to develop and implement a fundraising plan

- Communicate with and involve maintenance people at the school and with the school system’s facilities dept.

January

- Finalize design plans for selected project with help of a project advisor

- Finalize Budget

- Finalize logistics concerning milestones

February

- Schedule site preparation day

- Schedule planting day

- Schedule “Celebration” day

- Continue to contact collaborating organizations for additional resources (e.g., Department of Recreation & Parks, Mayors’ Office, etc.)

- Begin acquiring and ordering  materials you will need (including donation requests)

- Begin to recruit volunteers for the preparation and planting day

March

- Continue to recruit volunteers, contractors and/or “paid hands” as needed

- Inform media of upcoming event

- Brainstorm & create a schedule for the planting day; coordinate student participation. Map out how the day will transpire

- Organize donation/purchase and delivery of materials (e.g., plants, mulch, soil, etc.)

- Develop maintenance plan

Recruit individuals in accordance with the maintenance plan (Master Gardener programs, garden clubs, university students, and parents can be a great resource for maintenance during summer months)

April & May

- Finish organizing and readying materials

- Prepare site

- Plant the site

- Continue to recruit individuals in accordance with the maintenance plan

June

Monarch Butterfly

- Begin to implement maintenance plan

- Celebrate!

- Look to next year – keep an eye on funding opportunities

July

- Continue to implement maintenance plan

August

- Continue to implement maintenance plan